## Task Tracker
# | Task | Details | Completed | Notes
1 | Close the loop on CPMT-addressed queries | End-to-end workflow for escalated queries; users see CPMT's response; reply on same thread; no manual email chains. | Partial (MVP) | MVP shipped (staff-side close-the-loop): a dedicated "My Escalations" page (/escalations) lists every query the staffer reported / that was unanswered / answered from an obsolete doc, with status (Awaiting CPMT / CPMT replied / Reviewed) and the CPMT reply shown inline. A realtime bell + unread badge in the Query Bot header points to it; each item can open the original chat (read-only transcript). Flags now store userId; replies set seenByUser=false (clears on view). Original chat thread is left untouched. Remaining: staff reply-back to re-open a flag (Phase 2) and email/push (Phase 3, needs backend trigger). Coordinate w/ Tanmay. Update (5 Jul 2026): escalations are now two-way conversation threads (staff reply re-opens the flag as Pending; CPMT follow-ups notify the staffer), and duplicate escalations are answered in one action with per-staffer notifications. Update (6 Jul 2026): Phase 2 (staff reply-back re-opens the flag) is DONE via conversation threads (#9); duplicate escalations are answered in one action with per-staffer notification, and Outreach 'Mark Resolved' also closes the escalation + notifies the staffer. Remaining: Phase 3 email/push notifications (needs backend trigger).
2 | Auto-update query status in the outreach tracker | When CPMT saves a response, the tracker updates automatically; no manual status change. | Yes | respondToFlagged now auto-sets outreach to Resolved (+ contactedAt/resolvedAt) on respond. Live via onSnapshot.
3 | Route obsolete-document answers to CPMT | Obsolete-document-based answers also enter the review flow, not just unanswered queries. | Yes | ANSWERED_OBSOLETE now creates a flaggedQueries record (source=OBSOLETE) with the answer + obsolete doc title; shown in the queue.
4 | Make obsolete-document warnings more prominent | Clear visual treatment so users don't act on outdated guidance. | Yes | Amber 'Based on an outdated document' banner + tinted bubble in chat and All-Chats transcript; status badge + in-text caveat retained.
5 | Capture repeat flagged queries separately | Surface repeated escalations on same/similar topic; spot poor responses, missing SOPs, knowledge gaps. | Yes (v1) | v1 shipped: Flagged queue groups repeated escalations by exact query text (count >= 2) into a "Repeat topics" panel with a likely-cause hint (Missing SOP / Poor answer quality / Outdated SOP); click to filter. v2 (semantic/near-duplicate clustering) still pending discussion with Tanmay. Update (5 Jul 2026): repeat groups are now actionable — responding to one flag offers 'also send to N pending duplicates' (on by default): each duplicate gets the reply in its own thread, its own TAT, and notifies its staffer. Repeat-topic chips toggle the queue filter.
6 | Add user feedback on bot responses | Thumbs up/down; free text on negative; route poor feedback to CPMT review. | Yes | Thumbs persist + hydrate on reopen; dislike opens a modal and flags to CPMT (source=DISLIKE) with the comment; read-only indicator in All Chats.
7 | Ingest CPMT responses for future auto-answering | CPMT's response is ingested so similar future questions are answered automatically. | Yes | Done (5 Jul 2026): CPMT text responses are ingested into the knowledge base. Respond dialog has an 'Also add this answer to the knowledge base' checkbox (on by default); the Q&A is rendered as a small PDF and pushed through the normal ingest pipeline as an ACTIVE 'CPMT Clarification' document — listed in Documents (retaggable OBSOLETE), citable in chat with source preview. Question text is embedded verbatim, so similar future queries retrieve it and are auto-answered instead of re-flagged. Verified end-to-end: a previously-flagged repeat query ('what is ftl?') now routes ANSWERED_ACTIVE citing the clarification. Document responses were already ingested (#8).
8 | Ingest uploaded supporting documents during resolution | Documents uploaded while responding auto-ingest into the SOP repository. | Yes | Respond-with-document auto-ingests as an Active SoP (parse->embed->Qdrant->Storage->Firestore). Verified end-to-end.
9 | Build / refine unique query-thread experience | Per-query link/thread where CPMT responds, users see the response, follow-ups happen in one place; no email. | Yes | Done (6 Jul 2026): every escalation is a two-way conversation thread. Staff open it from My Escalations (/escalations/[id]) and can reply anytime — a reply re-opens the flag as Pending in the CPMT queue; CPMT replies from the hub (/hub/flagged/[id]) and the staffer is notified (bell + unread badge). The thread shows the original query, the bot answer under review (with citations/sources), and the full back-and-forth — no email. Legacy one-shot replies render as a single CPMT message.
10 | Support query management on the CPMT Hub side | Dashboard, flag queue, outreach tracker, management workflows in the separate CPMT Hub portal. | Yes | CPMT Hub (admin-only) has Dashboard, Flagged Queries, Outreach Tracker, Documents, All Chats, Monthly Report; staff see only the Query Bot.
11 | Improve reporting and downloadable reports | Generate (not just view) reports; by department / geography / role / query type. | Partial | Dashboard CSV export added (Query log, Flagged queue, Documents, Summary KPIs); query log includes department. Update (5 Jul 2026): dashboard Filters button with Department, Branch (geography proxy) and Query-status breakdowns — all KPIs/charts/exports respect them; Flagged queue gained the same consolidated filters incl. origin (Query Bot / Bank Form). Remaining: role-based breakdown (needs role denormalised onto query records).
12 | Refine document summarization capability | Better, more useful summaries for SOPs; flowcharts and visual representation. | Yes | Summaries restructured (Overview/Key Points/Process Flow); Process Flow renders as a Mermaid flowchart; full-page streaming view with Regenerate.
13 | Add document overlap / consolidation detection | On upload, compare to existing docs; highlight overlaps and consolidation candidates. | Yes | Done (6 Jul 2026): upload-time overlap detection in the CPMT Hub. On upload, the new document's chunks are compared against the ACTIVE corpus (one batched Qdrant query; chunk cosine >= 0.80, candidate flagged at >= 50% coverage). Strong overlaps pause the upload on a dedicated review page (/hub/documents/upload): each candidate shows % overlap with a severity label (near duplicate / strong / partial), clickable page chips open the existing PDF at the overlapping page, and 'Mark obsolete' retires superseded versions in the same action (Upload anyway / Cancel also available). Confirm reuses the cached parse+embeddings (no re-OCR/re-embed); the check fails open so a broken check never blocks uploads. Verified on the Deposit Policy version pair (V2.2 flagged at 84% when re-uploading V3.1). Testing surfaced 2 previously uncatalogued duplicates (Platina V3.0 double-ingest; NB36 copy of Deposit Policy V3.1) — added to docs/CORPUS-DUPLICATES.md. Out of scope: corpus-wide scan of already-ingested docs (cleanup stays manual per CORPUS-DUPLICATES.md). Update (7 Jul 2026): side-by-side compare added to the overlap review — clicking a candidate's 'Compare side by side' button or any overlapping-page chip opens a split viewer with the just-picked upload on the left (rendered locally from the browser, before anything is stored) and the existing document on the right, opened at the matching page pair. A stepper walks both panes through every (upload page ↔ existing page) match reported by the backend; each pane keeps its own page/zoom controls. .docx uploads show a fallback in the left pane (browsers can't render Word).
14 | Explore sync with Ujjivan systems | Doc storage access, DB integration, CPMT Hub <-> Ujjivan Connect sync; assess common data layer. | No | Not started — external/exploratory; needs Ujjivan enterprise/BA/technical teams.
15 | Evaluate AI assistance for bank forms | Search bank forms and return links; assess form guidance / sample-filling / correct-form linking. | Partial (POC) | POC shipped (4–6 Jul 2026) for the Vehicle Finance LAF: AI form assistant (staff + admin apps) that fills the form conversationally — extracts values from free text with server-side validation, answers policy questions from the SoP knowledge base with clickable citations and active/obsolete warnings, auto-flags unanswered questions to CPMT, supports thumbs feedback with full session-transcript review, resumable sessions, and generates a draft-filled PDF (values placed on the flat form incl. date slots; signatures/Form 60/bank-use manual). Field inventory in docs/vf-laf-field-inventory.md. Remaining: form search & correct-form linking across the full Form Center catalogue (~74 forms) and adding more forms to the engine (schema per form).